A picture containing drawing

Description automatically generated

Nibley City

**1300 West Improvements**

**from 3310 South to 3390 South**

Contract Documents and Specifications

Date: January 10, 2025

**PROJECT MANAGER**

Tom Dickinson, P.E.

City Engineer

425 West 3200 South

Nibley, UT 84321

435-757-9848

<tomd@nibleycity.gov>

**CIVIL ENGINEER**

Joseph Day P.E.

Civil Solutions Group, Inc.

801-624-0588

[jday@civilsolutionsgroup.net](mailto:jday@civilsolutionsgroup.net)

TABLE OF CONTENTS

[BID REQUEST 4](#_Toc160193896)

[INSTRUCTIONS TO BIDDERS 5](#_Toc160193897)

[PROPOSAL 8](#_Toc160193898)

[BID SCHEDULE 9](#_Toc160193899)

[MEASUREMENT AND PAYMENT 10](#_Toc160193900)

[CONTRACTOR QUALIFICATION FORM 16](#_Toc160193901)

[SCHEDULE FOR CONTRACT COMPLETION 17](#_Toc160193902)

[BID BOND 18](#_Toc160193903)

[NOTICE OF AWARD 20](#_Toc160193904)

[CONTRACT FOR CONSTRUCTION 22](#_Toc160193905)

[NIBLEY CITY INSURANCE AND BOND REQUIREMENTS 30](#_Toc160193906)

[PERFORMANCE AND PAYMENT BOND 32](#_Toc160193907)

[NOTICE TO PROCEED 35](#_Toc160193908)

[CHANGE ORDER FORM 36](#_Toc160193909)

[NOTIFICATION OF PROJECT COMPLETION 37](#_Toc160193910)

[GENERAL CONDITIONS AND SPECIAL PROVISIONS 38](#_Toc160193911)

# **BID REQUEST**

Sealed bids will be received by Nibley City at Nibley City Hall, 425 West 3200 South, until 2:00 pm, February 6th 2025, for:

***1300 West Improvements***

***From 3310 South to 3390 South***

Bid opening will be held immediately after the bid closure on the above date in the:

**Nibley City Hall Meeting Room**

Specifications are available on the Nibley City web page and on file in the office of the City Engineer, 625 West 3200 South, Nibley, Utah, and copies may be obtained by prospective bidders.

Contractors should be prepared to submit documentation with their PROPOSAL as outlined in the INSTRUCTIONS FOR BIDDERS as a part of a Contractor Qualification Process.

A Bid Bond, or cashier's check for 5% of bid, payable to Nibley City, must accompany each bid, along with a proposed SCHEDULE FOR CONTRACT COMPLETION. Upon award of the bid, a PAYMENT BOND and a PERFORMANCE BOND will be required for 100% of any bid which exceeds $5,000.

Questions regarding bid, please contact Tom Dickinson at tomd@nibleycity.gov

The right is reserved by Nibley City to reject any or all bids.

Dated this January 10, 2025

**INSTRUCTIONS TO BIDDERS**

Bids will be received by **NIBLEY CITY** (herein called "Owner"), at 425 West 3200 South, Nibley, Utah until **2:00 p.m.** on **February 6, 2025** and then immediately after the bid closure publicly opened and read aloud.

**During the Bidding period all questions pertaining to the project or bid shall be submitted in writing by February 3, 2025 @ 5:00 p.m. to** [**tomd@nibleycity.gov**](mailto:tomd@nibleycity.gov)**. The responses to these questions will be posted daily on the Nibley City website. The website address is:** [**https://nibleycity.com/public-works/**](https://nibleycity.com/public-works/)

Each Bid must be submitted in a sealed envelope addressed to Nibley City, 425 West 3200 South, Nibley, Utah. Each sealed envelope should bear on the outside the name of the project for which the bid is submitted. If forwarded by mail, the sealed envelope containing the Bid must be enclosed in another envelope addressed to the owner at the address above.

All Bids must be submitted on the required BID SCHEDULE. All blank spaces for unit prices and total costs must be filled in, in ink or typewritten, and the BID SCHEDULE must be fully completed showing the total of the bid and executed when submitted. Only one copy of the Bid Schedule is required.

Any Bid may be withdrawn prior to the above scheduled time for the opening of bids or authorized postponement thereof. Nibley City shall have possession of the bids at the designated time and location. Any Bid en-route, either in the mail or at other locations in the City; will not be considered timely and will be returned unopened. No Bidder may withdraw a Bid within 90 days after the actual date of the opening thereof. Should there be reasons why the contract cannot be awarded within the specified period, the time may be extended by mutual agreement between the Owner and the Bidder.

The Bidder shall submit as a part of their Bid the included CONTRACTOR QUALIFICATION FORM outlining experience of the Bidder on similar projects over the past three (3) years. This form will be used to help determine the qualifications of the Bidder. Any Bid which does not include a CONTRACTOR QUALIFICATION FORM exhibiting project experience funded by similar federal programs, shall be considered non-responsive and shall be returned to the BIDDER without being read.

Owner reserves the right to reject any and all Bids, to waive any and all informalities not involving price, time or changes in the Work and to negotiate contract terms with the successful Bidder, and the right to disregard all nonconforming, nonresponsive or conditional Bids. Also, Owner reserves the right to reject the Bid of any Bidder if Owner believes that it would not be in the best interest of the Project to make an award to that Bidder, whether because the Bid is not responsive or the Bidder is unqualified or of doubtful financial ability or fails to meet any other pertinent standard or criteria established by the Owner.

Each BID must include a detailed SCHEDULE FOR CONSTRUCTION COMPLETION showing the anticipated beginning date, the nature and sequence of construction activity including SWPPP implementation, obtaining permits, and the approximate completion date. The time to complete the work shall be less than or equal to the time allowed to complete the work as shown on the PROPOSAL form, but shall not exceed the time allowed for completion as shown on the PROPOSAL form. Any BID which does not include a SCHEDULE FOR CONSTRUCTION COMPLETION shall be considered non-responsive and shall be returned to the BIDDER without being read. If the TOTAL one or more BIDS submitted is within 5% of the lowest submitted BID, the bid may be awarded to the BIDDER with the earliest start time and/or the shortest, reasonable time for completion, as agreed upon by the Owner of the project.

Liquidated Damages are a part of this Contract. The only way to extend the completion date for a project is by CHANGE ORDER. If the work is not completed by the completion dates as set by the approved SCHEDULE FOR CONTRACT COMPLETION submitted, or as adjusted by CHANGE ORDER, Liquidated Damages will be imposed for every day, Sundays and City observed holidays excluded, that the work proceeds past the completion date, including time to complete the “Punch List” items.

Bidders must satisfy themselves of the accuracy of the estimated quantities in the BID SCHEDULE by examination of the site and review of the Drawings and Specifications including Addenda. After Bids have been submitted, the Bidder shall not assert that there was a misunderstanding concerning the quantities of work or of the nature of the work to be done.

The Owner shall provide to Bidders prior to bidding, all information which is pertinent to, and delineates and describes, the land owned and easements or rights‑of way acquired or to be acquired.

The Contract Documents contain the provisions required for the construction of the project. Information obtained from an officer, agent, or employee of the Owner or any other person shall not affect the risks or obligations assumed by the Contractor. All questions about the meaning or intent of the Contact Documents are to be directed to the Project Manager. Only questions answered by the formal written Addenda will be binding. Oral and other interpretations or clarifications will be without legal effect.

Each Bid must be accompanied by a BID BOND payable to the Owner for five percent of the total amount of the Bid. As soon as the bid prices have been compared, the Owner will return the Bid Bonds of all except the three lowest responsible Bidders. When the Contract for Construction is executed, the Bid Bonds of the two remaining unsuccessful Bidders will be returned. The Bid Bond of the successful Bidder will be retained until the Payment Bond and Performance Bond have been executed and approved, at which time it will be returned. A certified check may be used in lieu of a Bid Bond.

Attorneys‑in‑fact who sign Bid Bonds or Payment Bond and Performance Bond must file with each Bond a certified and effective dated copy of their power of attorney.

The party to whom the Project is awarded will be required to execute the CONTRACT FOR CONSTRUCTION and obtain the PERFORMANCE BOND AND PAYMENT BOND and PROOF OF INSURANCE within the (10) calendar days from the date when NOTICE OF AWARD is delivered to the Bidder. The NOTICE OF AWARD shall be accompanied by the necessary CONTRACT FOR CONSTRUCTION and Bond forms. In case of failure of the Bidder to execute the CONTRACT FOR CONSTRUCTION, the Owner may at his option consider the Bidder in default, in which case the BID BOND accompanying the Proposal shall become the property of the Owner.

The Owner within sixty days of receipt of acceptable PERFORMANCE BOND, PAYMENT BOND and CONTRACT FOR CONSTRUCTION signed by the party to whom the Contract was awarded shall sign the Contract and return to such party an executed duplicate of the Contract. Should the Owner not execute the Contract within such period, the Bidder may by written notice withdraw his signed Contract. Such notice of withdrawal shall be effective upon receipt of the notice by the Owner.

The NOTICE TO PROCEED shall be issued within ten (10) calendar days of the execution of the CONTRACT FOR CONSTRUCTION by the Owner. Should there be reasons why the NOTICE TO PROCEED cannot be issued within such period; the time may be extended by mutual agreement between the Owner and Contractor. If the NOTICE TO PROCEED has not been issued within the ten (10) day period or within the period mutually agreed upon, the Contractor may terminate the Contract without further liability on the part of either party.

The Owner may make such investigations as the Owner deems necessary to determine the ability of the Bidder to perform the work, and the Bidder shall furnish to the Owner all such information and data the Owner may request. The Owner may reject any Bid if the evidence submitted, or an investigation of such Bidder fails to satisfy the Owner that the Bidder will complete the work contemplated therein or if Bidder fails to furnish requested information.

A conditional or qualified Bid will not be accepted.

Award will be made according to Nibley City Code.

All applicable laws, ordinances, and rules and regulations of all authorities having jurisdiction over construction of the Project shall apply to the Contract throughout.

Each Bidder is responsible for inspecting the site and for reading and being thoroughly familiar with the Contract Documents, including SPECIAL PROVISIONS and the NIBLEY CITY ENGINEERING DESIGN STANDARDS AND SPECIFICATIONS. The failure or omission of any Bidder to do any of the foregoing shall in no way relieve any Bidder from any obligation in respect to his Bid.

**PROPOSAL**

Bids will be received at Nibley City, City Hall located at 425 West 3200 South, Nibley, Utah.

Dear Sir:

The undersigned, after having personally and carefully examined the Plans, Specifications and location which are a part hereof, proposes and agrees to furnish all materials, labor, equipment, and transportation necessary to install ready for service and to the satisfaction of the City Engineer for Nibley City, in accordance with the Plans and Specifications which are a part hereof, all items included in the **1300 West Improvements from 3310 South to 3390 South** in consideration of the unit prices totaling to the lump sum of $**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_** and further agree to complete the work withinthe time specified in the SCHEDULE FOR CONTRACT COMPLETION after being notified by the City Engineer to commence the work. Contractor further agrees to pay as liquidated damages, the sum of **$1,500** for each consecutive day after Final Completion dates noted in SCHEDULE FOR CONTRACT COMPLETION.

It is understood that the quantities stated are approximate only and are for the purpose of comparing Bids and fixing the amount of Bonds, and the payments will only be made on the basis of unit prices of the actual quantities, as determined by the Owner's Engineer in the completed work. It is further understood that the quantities will be increased or decreased as necessary to maximize the benefit of the existing budgets.

It is hereby agreed that Nibley City has the right to reject this proposal or to award the work to the undersigned at the sum stipulated, if action is taken within thirty (30) days after opening of Bids.

The Contractor hereby acknowledges receipt of the following Addenda:

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Date Contractor

**BID SCHEDULE**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Item** | **Description** | **Unit** | **Quantity** | **Unit Price** | **Item Price** |
| 1 | Mobilization | Lump Sum | 1 |  |  |
| 2 | Traffic Control | Lump Sum | 1 |  |  |
| 3 | Survey | Lump Sum | 1 |  |  |
| 4 | Storm Water Pollution Prevention Plan (SWPPP) | Lump Sum | 1 |  |  |
| 5 | Sawcut Existing Asphalt/Concrete | Lineal Foot | 547 |  |  |
| 6 | Remove Existing Concrete and Asphalt | Square Foot | 1,297 |  |  |
| 7 | Remove Existing Fence Line | Lineal Foot | 309 |  |  |
| 8 | Excavation/Site Fill and Preparation | Lump Sum | 1 |  |  |
| 9 | 3x3 Stormwater Junction Box | Each | 1 |  |  |
| 10 | 4x4 Stormwater Junction Box | Each | 2 |  |  |
| 11 | Construct 15-inch Concrete Piping | Lineal Foot | 43 |  |  |
| 12 | Construct 36-inch Concrete Piping | Lineal Foot | 79 |  |  |
| 13 | Construct Keystone Retaining Wall | Lineal Foot | 190 |  |  |
| 14 | Construct Curb Wall & Guardrail | Lineal Foot | 190 |  |  |
| 15 | Reinstall Fence | Lineal Foot | 309 |  |  |
| 16 | Compacted Base Course | Square Foot | 13,500 |  |  |
| 17 | Compacted Granular Borrow | Cubic Yard | 1,275 |  |  |
| 18 | Construct New Concrete Sidewalk | Square Foot | 4,387 |  |  |
| 19 | Construct Concrete Pavement at Approach | Square Foot | 130 |  |  |
| 20 | Construct Asphalt Pavement | Square Foot | 8,654 |  |  |
| 21 | Construct Curb and Gutter | Lineal Foot | 532 |  |  |
| 22 | Construct Park Strip Drainage Swale | Lineal Foot | 532 |  |  |
| 23 | Construct Irrigation Drainage Ditch | Lineal Foot | 194 |  |  |
| 24 | Install Fire Hydrant Assembly | Each | 1 |  |  |
| 25 | Landscaping and Irrigation | Lump Sum | 1 |  |  |
| 26 | Quality Control and Testing | Lump Sum | 1 |  |  |
| 27 | BID ALT – Install 2” Street Lighting Conduit per Rocky Mountain Power Requirements | Lineal Foot | 150 |  |  |
| 28 | ADDENDUM #1 – Install 36-inch flared end and trash grate | Lump Sum | 1 |  |  |
| 29 | ADDENDUM #2 – Remove existing 3x3 storm drain box | Lump Sum | 1 |  |  |

**MEASUREMENT AND PAYMENT**

**PART 1 GENERAL**

1.1 SECTION INCLUDES

General Description of Measurement and Payment

1.2 GENERAL ITEMS

* + 1. Units of measurement are listed in the bid schedule.

See measurement and payment procedures in APWA Section 01 29 00.

Unit of Measure: Refer to the measurement and bid item that identifies the unit of measurement to be used for unit price items.

1.3 SCHEDULE OF BID ITEMS

* + 1. MOBILIZATION
       1. Measurement will be lump sum complete. Payment shall be:
          1. 50% at first pay estimate; and
          2. 50% at final pay estimate
       2. Payment covers cost of mobilization, installation of all temporary facilities and bringing all necessary construction equipment to the site. Upon completion of the Work any unpaid amount of the original contract for the separate item of mobilization and temporary facilities will be paid. Also includes: any and all temporary facilities including but is not limited to water, power, fencing (permanent or temporary), fence removal as required, solid waste disposal, sanitation facilities, and any other temporary facilities or utilities, etc., and all other items not covered in other bid items.
    2. TRAFFIC CONTROL
       1. Measurement shall be lump sum complete. Payment shall be:

25% at first pay estimate;

50% at 75% completion pay estimate;

25% at final pay estimate.

* + - 1. Bid price includes cost of creating a traffic control plan by a certified traffic control technician in accordance with the Utah MUTCD, most current version, acceptable to Engineer, to provide a safe work zone including all vehicular, bicyclists, and pedestrian traffic. The contractor shall provide traffic control for this project and for utility providers performing work related to this project.
      2. Bid price includes cost of Nibley City Work in the Right of Way Permit.
    1. SURVEY
       1. Measurement shall be lump sum complete. Payment shall be:

25% at first pay estimate;

50% at 75% completion pay estimate;

25% at final pay estimate.

* + - 1. The unit price to be paid for this item shall be considered compensation in full for all labor, materials and equipment necessary to Provide Surveying for Project by a Licensed Surveyor to include survey control verification, construction staking, quantity verification, and as-built survey including the preparation and delivery of record drawings.
      2. Bid price includes all labor, products, tools, equipment, transportation, services and incidentals associated with establishing and providing survey and support for utility providers as needed for maintenance, relocation, new installation, etc. as part of this project.
    1. CREATE AND IMPLEMENT STORM WATER POLLUTION PREVENTION PLAN (SWPPP)
       1. Measurement will be lump sum complete.
       2. Payment shall be:

50% at first pay estimate; and

50% at final pay estimate

* + - 1. Payment covers all cost associated with preparation, in cooperation with Nibley City, and implementation of a storm water pollution prevention plan (SWPPP) and acceptable best management practices acceptable to Nibley City Storm Water Inspector throughout the duration of the project and until the site reaches ‘Permanent Stabilization”.
      2. Payment includes labor, materials, equipment, and costs associated with implementing and maintaining compliance with all requirements of the General Permit for Construction Dewatering and Hydrostatic Testing (UTG070000) as required by the State of Utah Division of Water Quality, Department of Environmental Quality, and payment includes all costs associated with design and implementation of collection, treatment, monitoring, inspecting, and testing requirements of the General Permit for Construction Dewatering and Hydrostatic Testing (UTG070000) as required by the State of Utah Division of Water Quality, Department of Environmental Quality.
      3. Bid price includes cost of: State of Utah Division of Water Quality NOI, NOT, and State of Utah Division of Water Quality Construction Dewatering and Hydrostatic Testing Permit if needed.
    1. SAWCUT EXISING ASPHALT/CONCRETE
       1. Measurement will be per lineal foot as needed to complete the project. No adjustment will be made for thickness.
       2. Bid price includes cost to saw cut existing concrete and/or asphalt at locations noted on plans.
       3. Asphalt and/or concrete is to be saw cut to full depth, no adjustment to be made for thickness of asphalt and/or concrete.
       4. Removal of additional asphalt and/or concrete as a result of contractor’s actions, lack of protection or contractor convenience is at contractor’s own expense.
    2. REMOVE EXISTING CONCRETE AND ASPHALT
       1. Measurement will be made by square foot of concrete and or asphalt removed.
       2. Bid price covers all labor, materials, tools, equipment, transportation, services, incidentals, and other cost to remove and dispose of existing concrete and/or asphalt at locations noted on plans. No price adjustment will be made for thickness.
       3. Existing asphalt is in poor condition. Additional asphalt removal and replacement has been calculated beyond that shown in the plans. This is to be completed as directed by Nibley City and paid per unit cost
    3. REMOVE EXISTING FENCE LINE
       1. Measurement will be by linear feet of fence removed. No adjustment will be made for material or type.
       2. Bid price covers cost to remove existing fence regardless of type. Included in this item are all labor, equipment and materials required for the removal of the existing fence.
    4. EXCAVATION/SITE FILL AND PREPARATION
       1. Measurement shall be lump sum complete.
       2. Bid price covers all labor, materials, tools, equipment, transportation, services, incidentals, and other items required to excavate, remove, transport, and dispose of excavated materials, organic materials, and preparation/fill of the site for placement of concrete, base, retaining wall, drive approaches, sidewalks, etc. to complete the project. Bid price includes cost of excavation, transport, and disposal of materials from the project to a location selected by Contractor.
       3. Excavation and site preparation for removal and/or installation of utilities is measured and paid as part of said utility.
       4. Contractor is responsible to excavate, remove, and dispose of all organic materials for a depth at least 6-inches and compaction of subgrades prior to placement of any fill or structural materials. No price adjustment will be made for thickness required to remove all organic materials.
    5. 3X3 STORMWATER JUNCTION BOX
       1. Measurement is by each with the measurement of junction box made by inside length and width. No adjustment will be made for depth.
       2. Bid price covers cost of work and material in constructing and installing
          1. Precast box -APWA as Amended by Nibley City Plan No. 332
          2. Structure and all components shall be HS-20 traffic rated.
       3. Bid price covers cost of incidental work such as saw cutting; additional excavation outside the typical trench section due to the additional size of the structure, connection to existing or new pipe, installation of concrete collars, adjustment of frame and cover to final grade, and placement of backfill.
       4. Bid price covers cost of supplying, installing, and compacting crushed aggregate base fill as leveling material and foundation material.
       5. Bid price includes cost of supplying and installing galvanized grate and frame.
       6. Bid price includes cost of making any and all connections to new and existing piping.
    6. 4X4 STORMWATER JUNCTION BOX
       1. Measurement is by each with the measurement of junction box made by inside length and width. No adjustment will be made for depth.
       2. Bid price covers cost of work and material in constructing and installing
          1. Precast box - APWA as Amended by Nibley City Plan No. 332
          2. Structure and all components shall be HS-20 traffic rated.
       3. Bid price covers cost of incidental work such as saw cutting; additional excavation outside the typical trench section due to the additional size of the structure, connection to existing or new pipe, installation of concrete collars, adjustment of frame and cover to final grade, and placement of backfill.
       4. Bid price covers cost of supplying, installing, and compacting crushed aggregate base fill as leveling material and foundation material.
       5. Bid price includes cost of supplying and installing galvanized grate and frame.
       6. Bid price includes cost of making any and all connections to new and existing piping.
    7. CONSTRUCT 15- INCH CONCRETE PIPING
       1. Measured per linear foot along center line of pipe.
       2. Bid price covers cost of incidental work and material such as removing interfering structures and obstructions, pipe fittings, connections, connecting to existing structures, de-watering, subgrade stabilization, shoring and bracing, and any temporary roadway or sidewalk surfacing materials.
       3. Bid price covers cost of excavation and installation of piping, and supplying, installing, and compacting bedding, foundation, pipe zone, and backfill material per APWA as Amended by Nibley City Plan No. 381 and Plan No. 382.
    8. CONSTRUCT 36- INCH CONCRETE PIPING
       1. Measured per linear foot along center line of pipe.
       2. Bid price covers cost of incidental work and material such as removing interfering structures and obstructions, pipe fittings, connections, connecting to existing structures, de-watering, subgrade stabilization, shoring and bracing, and any temporary roadway or sidewalk surfacing materials.
       3. Bid price covers cost of excavation and installation of piping, and supplying, installing, and compacting bedding, foundation, pipe zone, and backfill material per APWA as Amended by Nibley City Plan No. 381 and Plan No. 382.
    9. CONSTRUCT KEYSTONE RETAINING WALL
       1. Measured per lineal foot of keystone retaining wall complete. No adjustment will be made for height of wall.
       2. Bid price covers cost of work and material to install keystone retaining wall in accordance with plan, details, and notes.
       3. Keystone wall layout and material shall be approved by City prior to acceptance and delivery.
    10. CONSTRUCT CURBWALL AND GUARDRAIL
        1. Measured per lineal foot of curbwall and guardrail complete.
        2. Bid price covers cost of work and material to construct curb wall and guardrail in accordance with plan, details, and notes.
        3. Guardrail embedment and installation shall be approved by City prior to acceptance.
    11. REINSTALL FENCE
        1. Measured per lineal foot of fence installed.
        2. Bid price covers cost of work and material to install fence line in accordance with plan, details, and notes. Bid price includes replacement of any
        3. Guardrail embedment and installation shall be approved by City prior to acceptance.
    12. COMPACTED BASE COURSE
        1. Measurement is per square foot compacted in place for areas supporting sidewalk, driveways, asphalt pavement, and other areas noted on plans. Depths at each constructed element shall be in accordance with plans, specifications and details, and will match existing depth where applicable.
        2. UTBC used for installation of underground utilities is not included in this bid item and shall be measured and paid under each utility.
        3. The correct depth and placement shall be verified and accepted by the City prior to placement of concrete or other structure.
        4. Payment shall be verified by submission of weigh tickets. Payment will not be made for locations not directed by ENGINEER.
        5. Bid Price includes all work necessary to comply with APWA Specifications and Plans as Amended by Nibley City.
        6. All density testing and core sampling and repairs shall be paid for under “QUALITY CONTROL AND TESTING.”
    13. COMPACTED GRANULAR BURROW
        1. Measurement is per cubic yard compacted in place for areas supporting asphalt pavement, and other areas noted on plans. Depths at each constructed element shall be in accordance with plans, specifications and details, and will match existing depth where applicable.
        2. The correct depth and placement shall be verified and accepted by the City prior to placement of base course or asphalt pavement.
        3. Payment shall be verified by submission of weigh tickets. Payment will not be made for locations not directed by ENGINEER.
        4. Bid Price includes all work necessary to comply with APWA Specifications and Plans as Amended by Nibley City.
        5. All density testing and core sampling and repairs shall be paid for under “QUALITY CONTROL AND TESTING.”
    14. CONSTRUCT NEW CONCRETE SIDEWALK
        1. Measured by square foot.
        2. Measurement of sidewalk through driveways will be paid for as part of CONSTRUCT CONCRETE APPROACH.
        3. Bid price covers cost of work and material to place sidewalk per APWA as Amended by Nibley City Plan No. 231.
        4. Included in costs are concrete, compaction, and other items incidental to placing concrete sidewalk to lines and grades shown on plans.
        5. Bid Price includes all work necessary to comply with APWA Specifications and Plans as Amended by Nibley City.
    15. CONSTRUCT CONCRETE APPROACH
        1. Measured by the square foot for depth 8 inches thick for sidewalks and aprons located within driveways, lanes, and access areas. This includes ramp, flares, aprons, sidewalk, etc.
        2. Included in costs are concrete, compaction, and other items incidental to placing concrete sidewalk to lines and grades shown on plans.
        3. Bid Price includes all work necessary to comply with APWA Specifications and Plans as Amended by Nibley City.
    16. CONSTRUCT ASPHALT PAVEMENT
        1. Asphalt mix shall be HMA PG 58-28, 1/2” MIX in accordance with APWA Standards and Specifications as amended by Nibley City.
        2. Measured and paid by square foot installed at locations shown on plan set. Thickness shall match existing thicknesses and shall be 4-inches minimum.
        3. Bid price includes cost of labor, materials, and equipment to provide and place asphalt pavement in accordance to the grades and matching existing asphalt depth with minimum thickness of 4-inches.
        4. All density testing and core sampling and repairs shall be paid for under “QUALITY CONTROL AND TESTING.”
        5. Bid price includes tackifier at all vertical joints and between lifts.
        6. Engineer shall approve asphalt depth prepared prior to asphalt being ordered or placed to ensure compliance with plans.
        7. Bid Price includes all work necessary to comply with APWA Specifications and Plans as Amended by Nibley City.
        8. Existing asphalt is in poor condition. Additional asphalt removal and replacement has been calculated beyond that shown in the plans. This is to be completed as directed by Nibley City and paid per unit cost.
    17. CONSTRUCT CURB AND GUTTER
        1. Measured by lineal foot.
        2. Bid price includes all labor, materials, tools, equipment, transportation services and incidentals associated with constructing curb and gutter in accordance with plans, specifications and details at locations shown on plans.
        3. Included in costs are concrete, compaction, and other items incidental to placing concrete curb and gutter to lines and grades shown on plans.
        4. Bid Price includes all work necessary to comply with APWA Specifications and Plans as Amended by Nibley City.
    18. CONSTRUCT PARKSTRIP DRAINAGE SWALE
        1. Measured by lineal foot of drainage swale installed.
        2. Bid price covers cost of work and material to construct drainage swale at locations shown on plans.
        3. Landscape at drainage swale will be paid under separate bid item.
        4. Drainage Swales shall be installed in accordance with Section 6 of the Nibley City Design Standards and Specifications with contours and slopes to retain runoff and/or facilitate a drainage path to existing and new piping where applicable.
    19. CONSTRUCT IRRIGATION DRAINAGE DITCH
        1. Measured by lineal foot of drainage ditch constructed.
        2. Bid price covers cost of work and material to construct drainage ditch at locations shown on plans.
        3. Drainage ditch to be seeded with natural seed mix approved by Nibley City Engineer.
    20. INSTALL FIRE HYDRANT ASSEMBLY
        1. Measurement is by each.
        2. Bid price covers cost of work and material in constructing and installing
           1. Fire Hydrant Assembly per detail 10/C501
           2. Installation per Nibley City Engineering Design Standards updated 03-23-2023
        3. Bid price covers cost of incidental work such as saw cutting; additional excavation outside the typical trench section, connection to existing or new pipe, installation of pipe, assembly, valves, restraints, placement of backfill and all other necessary work required to install the fire hydrant assembly per Nibley City Standards.
    21. LANDSCAPING AND IRRIGATION
        1. Measurement shall be lump sum complete. Payment shall be:

10% at first pay estimate;

50% at 75% completion pay estimate;

40% at final pay estimate.

* + - 1. Bid price includes all labor, materials, tools, equipment, transportation services and incidentals associated with installing all landscape and irrigation items in accordance with plans, specifications and details at locations shown on plans.
      2. Bid price includes replacement of landscaping in kind as replacement of disturbed existing landscaping. Disturbed landscaping shall be replaced with the same; ie. rock at areas where rock previously existed, grass where grass previously existed, etc.
      3. Bid price includes all labor, materials, tools, equipment, transportation, services and incidentals associated with providing rock (where applicable) and/or top soil, seeding or laying sod, modifying, and adjusting existing underground irrigation systems where applicable.
      4. Bid price includes restoration of existing irrigation systems including heads, rotors, boxes, and valve where applicable.
      5. Refer to APWA Specifications as Amended by Nibley City.
    1. QUALITY CONTROL AND TESTING
       1. Measurement and payment will be made per lump sum for all quality control testing, complete.
       2. Payment shall be:

25% at first pay estimate; and

Remaining portion of bid item paid as percentage of the contract completed.

* + - 1. Bid price covers all labor, equipment and materials, including subcontractors, required to verify and ensure the quality of the installed project including, but not limited to, proctor, gradation, CBR values, compaction testing of the subgrade, untreated base course and granular borrow, concrete testing, asphalt density, asphalt core samples (if needed), and all other testing required by the most recent edition of APWA Standard Specifications as amended by Nibley City.
    1. BID ALT – INSTALL 2” STREET LIGHTING CONDUIT
       1. Measured per linear foot along center line of conduit.
       2. Bid price covers cost of incidental work and material such as removing interfering structures and obstructions, pipe fittings, connections, connecting to existing structures, de-watering, subgrade stabilization, and any roadway or sidewalk surfacing materials.
       3. Bid price covers cost of excavation/trenching and installation of conduit, and supplying, installing, and compacting backfill material.
       4. Installation to meet Rocky Mountain Power Standards and Specifications.
    2. ADDENDUM #1 – INSTALL 36-INCH FLARED END AND TRASH GRATE
       1. Measurement shall be lump sum complete
       2. Bid price covers cost of work and material in constructing and installing
          1. Pipe Outfall Round with Flare – APWA as Amended by Nibley City Pla No 323.1
          2. Prefabricated Trash Grate per industry standard.
       3. Bid price covers cost of incidental work such as additional excavation outside the typical trench section, connection to existing or new pipe, adjustment and leveling of pipe end, frame and trash grate to final grade and contouring and final grading.
       4. Bid price covers cost of supplying, installing, and compacting crushed aggregate base fill as leveling material and foundation material.
       5. Bid price includes cost of supplying and installing galvanized grate and frame.
       6. Bid price includes cost of making any and all connections to new and existing pipe.
    3. ADDENDUM #2 – REMOVE EXISTING 3X3 STORM DRAIN BOX
       1. Measurement shall be lump sum complete
       2. Bid price covers cost to remove existing structure. Included in this item are all labor, equipment and materials required for the removal of the existing storm drain box.

Bid price covers all incidental work and tools, equipment, transportation, services, and other items required to excavate, remove, transport, and dispose of existing storm drain box.

**CONTRACTOR QUALIFICATION FORM**

(List similar projects funded by similar federal funding completed by the Contractor over the past three (3) years)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| NAME / DATE OF PROJECT | DOLLAR AMOUNT OF PROJECT | OWNER REFERENCE  (NAME AND TELE NO.) | INVOLVEMENT OR ROLE IN PROJECT | COMPLETION | |
| ON TIME  (YES/NO) | WITHIN BUDGET  (YES/NO) |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |

**SCHEDULE FOR CONTRACT COMPLETION**

TO BE COMPLETED BY CONTRACTOR

Contractor shall provide a detailed Gantt chart or other schedule including all critical dates from notice of award to the final construction approval and a detailed critical path.

**Substantial Completion**- The Work will be substantially completed on or before **September 15, 2025**

**Final Completion**- The Work will be completed and ready for final payment in accordance with Section 6.03 of the CONTRACT FOR CONSTRUCTION on or before **October 15, 2025.**

# BID BOND

KNOW ALL MEN BY THESE PRESENTS, that we, the undersigned, as Principal, and as Surety, are hereby held and firmly bound unto as OWNER in the penal sum of for the payment of which, well and truly to be made, we hereby jointly and severally bind ourselves, successors, and assigns. Signed, this day of , 20 . The Condition of the above obligation is such that whereas the Principal has submitted to a certain BID, attached hereto and hereby made a part hereof to enter into a contract in writing, for the

***1300 WEST IMPROVEMEMTS***

***FROM 3310 SOUTH TO 3390 SOUTH***

NOW, THEREFORE,

(a) If the BID shall be rejected, or

(b) If said BID shall be accepted and the Principal shall execute and deliver a contract in the Form of Contract attached hereto (properly completed in accordance with said BID) and shall furnish a BOND or bonds for his faithful performance of said contract, and for the payment of all persons performing labors and furnishing materials in connection therewith, and shall in all other respects perform the agreement created by the acceptance of said BID.

then this obligation shall be void, otherwise the same shall remain in force and effect; it being expressly understood and agreed that the liability of the Surety for any and all claims hereunder shall, in no event, exceed the penal amount of this obligation as herein stated. The Surety, for value received, hereby stipulates and agrees that the obligations of said Surety and its BOND shall be in no way impaired or affected by any extension of the time within which the OWNER may accept such BID; and said Surety does hereby wave notice of any such extension.

IN WITNESS WHEREOF, the Principal and the Surety have hereunto set their hands and seals, and such of them as are corporations have caused their corporate seals to be hereto affixed and these presents to be signed by their proper officers, the day and year first set forth above.

(L.S.)

Principal

Surety

By:

IMPORTANT - Surety companies executing BONDS must appear on the Treasury Department’s most current list (Circular 570 as amended) and be authorized to transact business in the state where the project is located.

# **NOTICE OF AWARD**

TO:

PROJECT DESCRIPTION:

***1300 WEST IMPROVEMEMTS***

***FROM 3310 SOUTH TO 3390 SOUTH***

The Owner has considered the Bid submitted by you for the above described work and you are hereby notified that your bid has been accepted for items in the amount of $\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

You are required by the Instructions to Bidders to execute the Contract for Construction and furnish the required Contractor’s Performance Bond, Payment Bond and certificates of insurance within ten (10) calendar days from the date of this Notice to you.

If you fail to execute said Contract or to furnish said Bonds within ten (10) days from the date of this Notice, said Owner will be entitled to consider all your rights arising out of the Owner’s acceptance of your Bid as abandoned and as forfeiture of your Bid Bond. The Owner will be entitled to such other rights as may be granted by law.

You are required to return an acknowledged copy of this Notice of Award to the Owner.

The instructions in Paragraph 2.5 of Section 00 72 00 of the APWA Manual of Standard Specifications are expected to be complied with as part of this project. This information is included as Attachment A.

Dated this , 20\_\_\_.

Owner: Nibley City, Utah

By:

Title:

**ACCEPTANCE OF NOTICE**

Receipt of the above Notice of Award is hereby acknowledged.

This day of , 20\_\_\_.

By:

Title:

Attachment A

APWA Manual of Standard Specifications

2017 Edition

Section 00 72 00

Paragraph 2.5

2.5 **BEFORE STARTING CONSTRUCTION**

A. **In General**: Before starting each part of the Work, CONTRACTOR shall carefully study and compare the Contract Documents and check and verify pertinent figures shown thereon and all applicable field measurements. CONTRACTOR shall promptly report in writing to ENGINEER any conflict, error or discrepancy that CONTRACTOR may discover and shall obtain a written interpretation or clarifications from ENGINEER before proceeding with any work affected thereby.

B. **Submittals:** Within 10 Days after the Effective Date of the Construction Contract, CONTRACTOR shall submit to ENGINEER, in reasonable detail and form acceptable to ENGINEER, copies of the following documents.

1. **Preliminary Progress Schedule**: The preliminary progress schedule shall show starting and completion dates for each construction sequence and:

a. submittal dates and dates required for approved submittals for shop drawings, product data and samples;

b. decision dates for products specified by allowances, selection of finishes and critical material or equipment release orders;

c. product procurement and delivery dates;

d. holiday cleanup preparations, And

e. specific dates for all special Inspections required prior to any utilities "turn-on" including temporary power.

2. **Preliminary Shop Drawing Schedule:** A supplemental schedule to the preliminary progress schedule shall show all Shop Drawing submissions required for the Work.

3. **Preliminary Schedule of Values:** The preliminary schedule of values (for Lump Sum Work), which includes provisions set forth in quantities and prices of items aggregating the Contract Price, shall subdivide the Work into component parts in sufficient detail to serve as the basis for progress payments during construction. Such prices will include an appropriate amount of overhead and profit applicable to each item of work. Bond expense shall not be prorated, but shall be shown as a separate item.

4. **Mobilization Program:** The site mobilization program shall allow for field office and trailer locations, material storage locations, power requirements for trailers, if any, and sanitary facilities.

5. **Permits:** The listing of, and photocopies of permits that the CONTRACTOR is required to purchase and maintain in accordance with Article 6.7.

6. **Quality Control Program:** The written program for the control of product quality and workmanship.

7. **Safety and Protection Plan:** The safety and protection plan shall comply with Article 6.12.

C. **Field Office:** When specified, the CONTRACTOR shall establish and maintain a field office in such a location that ENGINEER may always contact CONTRACTOR for transmittal of Plans, instructions and dissemination of Project information. Unless waived by ENGINEER, CONTRACTOR shall provide and maintain a telephone and facsimile machine in the field office during work performance.

**CONTRACT FOR CONSTRUCTION**

**This Contract** is by and between Nibley City (hereinafter called the OWNER)

and (hereinafter called CONTRACTOR)

OWNER and CONTRACTOR, in consideration of the mutual covenants hereinafter set forth, agree as follows:

**ARTICLE 1 – THE PROJECT**

* 1. The Project for which the Work under the Contract Documents shall apply is generally described as follows:

***1300 WEST IMPROVEMENTS FROM 3310 SOUTH TO 3390 SOUTH***

* *Construct new road including curb, gutter, and sidewalk*
* *Keystone gravity retaining wall*
* *Driveway restoration*
* *Irrigation/storm drain piping and structures*
* *Drainage swales*
* *Landscape restoration*
  1. **ARTICLE 2 – WORK**
  2. CONTRACTOR shall complete all Work as specified or indicated in the Contract Documents for completion of the project.
  3. CONTRACTOR shall adhere to all road construction safety rules including but not limited to requirements found in the Manual of Uniform Traffic Control Devices (MUTCD) as adopted by the State.

**ARTICLE 3 – ENGINEER**

* 1. The ENGINEER, unless otherwise indicated in the Contract Documents, shall be the CITY ENGINEER, or his appointed representative.

**ARTICLE 4 – CONTRACT TIMES**

* 1. Time of the Essence:

1. All time limits for Milestones, if any, Substantial Completion, and completion and readiness for final payment as stated in the Contract Documents are of the essence of the Contract.
   1. Dates for Substantial Completion and Final Payment:
2. The Work will be substantially completed on or before **September 15, 2025**
3. The Work will be completed and ready for final payment in accordance with Section 6.03 on or before **October 15,** **2025.**

4.03 Liquidated Damages:

A. CONTRACTOR and OWNER recognize that time is of the essence of this Agreement and the OWNER will suffer financial loss if the Work is not completed within the times specified in paragraph 4.02, plus any extensions thereof allowed in accordance with the General Conditions. The parties also recognize that it will be impracticable to determine actual damages which OWNER will sustain in the event of or by reason of the delay. Accordingly, instead of requiring any such proof, OWNER and CONTRACTOR agree that as liquidated damages for delay (but not as a penalty) CONTRACTOR shall pay OWNER $ 1,500.00 for each day that expires after the specified time in paragraph 4.02 for substantial completion until the Work is substantially complete. After substantial completion, if CONTRACTOR shall neglect, refuse, or fail to complete the remaining Work within the Contract time or any proper extension thereof granted by OWNER, CONTRACTOR shall pay OWNER $ 1,500.00 for each day that expires after the times specified in paragraphs 4.02 and 6.03 for completion and readiness for the final payment until the Work is completed and ready for final payment. It is further agreed that the amount stipulated for liquidated damages per day of delay is a fair and reasonable estimate of the damages that would be sustained by OWNER, and CONTRACTOR agrees to pay such liquidated damages as herein provided. In case the liquidated damages are not paid, CONTRACTOR agrees that OWNER may deduct the amount thereof from any money due or that may become due to CONTRACTOR by progress payments or otherwise under the Agreement, or if said amount is not sufficient, recover the total amount.

1. In the event CONTRACTOR shall neglect, refuse, or fail to complete any remaining Work within the Contract time or any proper extension thereof granted by OWNER, OWNER may elect to terminate the Contract by written notice to Consultant.
   1. If the Contract is not terminated, CONTRACTOR shall continue performance and completion of the Work and be liable to the City for the liquidated damages until the Work is complete and acceptable under the Contract; and
   2. In the event OWNER exercises its right of termination under this section, CONTRACTOR shall be liable to OWNER for liquidated damages until such time OWNER may reasonably obtain completion of the WORK by other reasonable means.

**ARTICLE 5 – CONTRACT PRICE**

5.01 OWNER shall pay CONTRACTOR FOR COMPLETION OF THE Work in accordance with the Contract Documents an amount in current funds equal to the sum of the amounts determined pursuant to paragraph 5.01.A below:

A. For all Work, the sum of:

$

(use words) (use figures)

**ARTICLE 6 – PAYMENT PROCEDURES**

* 1. Submittal and Processing of Payments:

A. CONTRACTOR shall submit Applications of Payment in accordance with the General Conditions. Applications for Payment will be processed by ENGINEER as provided in the General Conditions.

6.02 Progress Payments; Retainage:

A. OWNER shall make progress payments on account of the Contract Price on the basis of CONTRACTOR’s Applications for Payment once each month during performance of the Work as provided in paragraphs 6.02.A.1 and 6.02.A.2 below. All payments will be made based on the percentage of job completion, and will be verified by Engineer prior to invoicing:

1. Prior to Substantial Completion, progress payments will be made in an amount equal to the percentage indicated below but, in each case, less the aggregate of payments previously made and less such amounts as ENGINEER may determine or OWNER may withhold, in accordance with the General Conditions:
   1. The OWNER will pay the CONTRACTOR a progress payment on the basis of the approved partial payment estimate submitted by the CONTRACTOR and verified by the ENGINEER, including any approved Change Orders, but will not hold retainage.
2. Upon Substantial Completion of the project, the OWNER will pay to 95 percent of the revised contract amount including any approved Change Orders.
   1. Final Payment
      * 1. Items noted on the ‘Punch’ or Completion List (List) shall be completed within 15 days unless otherwise agreed upon by both the OWNER and CONTRACTOR. Unless an extension is agreed to by both the OWNER and CONTRACTOR, failure to complete the ‘List’ within 15 days will constitute failure to meet requirements of Substantial Completion resulting in possible Liquidated Damages as described in section 4.03.
        2. When all items on any generated ‘Punch’ or Completion List have been completed, the OWNER will pay the remaining 5 percent of the revised contract amount within 30 days of notification to the OWNER in writing by the CONTRACTOR that all items have been completed. The OWNER shall verify that all items have been completed before final payment is made.

**ARTICLE 7 – INTEREST**

* 1. All moneys not paid when due as provided in the General Conditions shall bear interest at the same rate that OWNER’s funds accrue interest in the State’s treasury account.

**ARTICLE 8 – CONTRACTOR’S REPRESENTATIONS**

* 1. In order to induce OWNER to enter into this Agreement, CONTRACTOR makes the following representations:

A. CONTRACTOR has examined and carefully studied the Contract Documents and the other related data identified in the Bidding Documents.

* + - 1. CONTRACTOR has visited the Site and become familiar with and is satisfied as to the general, local, and Site conditions that may affect the cost, progress, and performance of the Work.
      2. CONTRACTOR is familiar with and is satisfied as to all federal, state, and local Laws and Regulations that may affect cost, progress, and performance of the Work.
      3. CONTRACTOR has carefully studied all: (1) reports of explorations and tests of subsurface conditions at or contiguous to the Site and all drawings of physical conditions in or relating to existing surface or subsurface structures at or contiguous to the Site (except Underground Facilities) which have been identified in the Supplementary Conditions as provided in the General Conditions and (2) reports and drawings of a Hazardous Environmental Condition, if any, at the Site which is identified in the Supplementary Conditions as provided in the General Conditions..
      4. CONTRACTOR has obtained and carefully studied (or assumes responsibility for having done so) all additional or supplementary examinations, investigations, explorations, tests, studies, and data concerning conditions (surface, subsurface, and Underground Facilities) at or contiguous to the Site which may affect cost, progress, or performance of the Work or which relate to any aspect of the means, methods, techniques, sequences, and procedures of construction to be employed by CONTRACTOR, including applying the specific means methods, techniques, sequences, and procedures of construction, if any, expressly required by the Contract Documents to be employed by CONTRACTOR, and safety precautions and programs incident thereto.
      5. CONTRACTOR does not consider that any further examinations, investigations, explorations, tests, studies or data are necessary for the performance of the Work at the Contract Price, within the Contract Times, and in accordance with the other terms and conditions of the Contract Documents.
      6. CONTRACTOR is aware of the general nature of work to be performed by OWNER and others at the Site that relates to the Work as indicated in the Contract Documents.
      7. CONTRACTOR has correlated the information known to CONTRACTOR, information and observations obtained from visits to the Site, reports and drawings identified in the Contract Documents, and all additional examinations, investigations, explorations, tests, studies, and data with the Contract Documents.
      8. CONTRACTOR has given ENGINEER written notice of all conflicts, errors, ambiguities, or discrepancies that CONTRACTOR has discovered in the Contract Documents, and the written resolution thereof by ENGINEER is acceptable to CONTRACTOR.
      9. CONTRACTOR agrees to register and participate in the Status Verification System to verify the work eligibility status of the CONTRACTOR's new employees that are employed in the state as set forth in Utah Code Section 63G-12-302. Each contractor or subcontractor who works under or for another contractor shall certify to the main contractor by affidavit that the contractor or subcontractor has verified through the Status Verification System the employment status of each new employee of the respective contractor or subcontractor.
      10. The Contract Documents are generally sufficient to indicate and convey understanding of all terms and conditions of performance and furnishing of the work.

**ARTICLE 9 – CONTRACT DOCUMENTS**

* 1. Contents:

1. The Contract Documents consist of the following:

1. Instructions to Bidders

2. Bid Bond

3. This Agreement

4. Performance Bond

5. Payment Bond

6. General Conditions, Document 00 72 00 of the APWA Manual of Standard Specifications, 2017 Edition, as modified by the City and herein.

7. Special Provisions including conditions of grant documents.

8. APWA Manual of Standard Specifications, including Standard Drawings

9. Nibley City Standards and Specifications, including Standard Drawings

10. Addenda (numbers to , inclusive)

11. Insurance and Bond Requirements

12. Exhibits to this Agreement (enumerated as follows):

a. Proposal

b. Bid Schedule

1. Schedule of Values (for Lump Sum Bid)
2. Measurement and Payment
3. Schedule of Project Completion
4. Contractor Qualification Form
5. Certificate of Insurance, approved by OWNER’s Attorney

13. The following which may be delivered or issued on or after the Effective Date of the Agreement and are not attached hereto:

* + 1. Notice of Award
    2. Notice to Proceed
    3. Written Amendments
    4. Change Orders
    5. Field Orders

1. There are no Contract Documents other than those listed above in this Article 9.
2. The Contract Documents may only be amended, modified or supplemented as provided in the General Conditions.

**ARTICLE 10 – MISCELLANEOUS**

* 1. Terms:

Terms used in this Agreement will have the meanings indicated in the General Conditions

10.02 Assignment of Contract:

No assignment by a party hereto of any rights under or interests in the Contract will be binding on another party hereto without the consent of the party sought to be bound; and specifically but without limitation, moneys that may become due and moneys that are due may not be assigned without such consent (except to the extent that the effect of this restriction may be limited by law), and unless specifically stated to the contrary in any written consent to an assignment, no assignment will release or discharge the assignor from any duty or responsibility under the Contract Documents.

10.03 Successors and Assigns:

OWNER and CONTRACTOR each binds itself, its partners, successors, assigns, and legal representatives to the other party thereto, its partners, successors assign and legal representatives in respect to all covenants, agreements, and obligations contained in the Contract Documents.

* 1. Termination for OWNER’s Convenience:

A. Upon ten (10) days’ written notice to CONTRACTOR, OWNER may, without cause and without prejudice to any other right or remedy of OWNER, terminate the Contract. In such case, CONTRACTOR shall be paid for (without duplication of any payment amounts or work items):

1. completed and acceptable Work executed prior to the effective date of termination, in accordance with the payment provisions of the Contract Documents; provided, however, that no completed work items shall be paid on a cost-plus basis;

2. reasonable expenses sustained prior to the effective date of termination in performing services and furnishing labor, materials, or equipment as required by the Contract Documents in connection with uncompleted Work or unacceptable Work (but only those portions of the unacceptable Work that are acceptable and CONTRACTOR shall not be entitled to any compensation for any portions of the Work which are unacceptable), plus fair and reasonable sums for overhead and profit on such expenses; provided, however, that CONTRACTOR shall not be entitled to additional compensation for Work items paid under subparagraph 10.04 A.1. above;

3. costs incurred in settlement of terminated contracts with Subcontractors, Suppliers, and others; provided, however, that CONTRACTOR shall not be entitled to additional compensation for Work items paid under subparagraphs 10.04 A.1. and 2. above; and

4. reasonable expenses directly attributable to termination; provided, however, that CONTRACTOR shall not be entitled to additional compensation for Work items paid under subparagraphs 10.04 A. 1., 2. and 3. above.

B. CONTRACTOR shall not be paid on account of loss of anticipated profits or revenue or other economic loss arising out of or resulting from such termination. Termination under this Subparagraph 10.04 shall not entitle CONTRACTOR to compensation on a cost-plus basis except for items paid under Subparagraph 10.04 A. 2. above.

C. This Article 10.04 shall amend the General Conditions, Document 007200 referenced in Article 9.01 A. 6. by replacing the “Termination for Owner’s Convenience” clause contained in 15.2 F. therein.

10.05 Severability:

Any provision or part of the Contract Documents held to be void or unenforceable under any Law or Regulation shall be deemed stricken, and all remaining provisions shall continue to be valid and binding upon OWNER and CONTRACTOR, who agree that the Contract Documents shall be reformed to replace such stricken provision of part thereof with a valid and enforceable provision that comes as close as possible to expressing the intention of the stricken provision.

10.06 Guarantee Period

The CONTRACTOR agrees to indemnify and save harmless the OWNER from any and all defects appearing or developing in the workmanship or materials performed or furnished under the Contract for a period of **one (1) year after** the date of the written notice from the Engineer recommending final acceptance of the entire project by the OWNER.

10.07 Counterparts:

This Agreement may be executed in counterparts, each of which shall be deemed an original but all of which shall constitute one and the same instrument.

IN WITNESS WHEREOF, the Parties have duly caused this Agreement to be executed on their respective behalves.

This Agreement will be effective on , 20\_\_\_.

OWNER: CONTRACTOR:

By: By:

Attest: Attest:

Address for giving notices: Address for giving notices:

END OF DOCUMENT

**NIBLEY CITY INSURANCE AND BOND REQUIREMENTS**

**FOR: 1300 WEST IMPROVEMENTS FROM 3310 SOUTH TO 3390 SOUTH**

The Contracting party shall procure and maintain for the duration of the contract insurance and bonds against claims or liability which arises out of or in connection with the performance of the work hereunder by the Contracting party, his agents, representatives, employees or subcontractors. The cost of such insurance and bonds shall be included in the Contracting party's bid or proposal.

**A. MINIMUM LIMITS OF INSURANCE**

Contracting party shall maintain limits not less than:

1. **GENERAL LIABILITY**: $2,000,000 combined single limit per occurrence, personal injury and property damage, $3,000,000 aggregate. Broad Form Commercial General Liability is required. (ISO 1993 or better) to include Products ‑ Comp/OP aggregate of $2,000,000. Limits to apply to this project individually.

2. **PROFESSIONAL LIABILITY:** Not applicable to this project.

3. **AUTOMOBILE LIABILITY**: $2,000,000 per occurrence. "Any Auto" coverage is required.

4. **WORKERS' COMPENSATION and EMPLOYERS LIABILITY**: Workers' Compensation statutory limits as required by the Workers Compensation Act of the State of Utah and Employers Liability limits at a minimum of $100,000 per occurrence.

5. **PAYMENT and PERFORMANCE BONDS:** Contracting party shall provide payment and performance bonds in a form acceptable to the City and in the full amount of the contract.

**B. ACCEPTABILITY OF INSURERS**

Insurance and bonds are to be placed with insurers admitted in the State of Utah with an A. M. Best rating of not less than A‑: IX, and in the limits as listed in this document, unless approved by the City’s Risk Manager, or his designee, **a minimum of five (5) business days prior to bid or proposal deadline**.

**C. NOTICE OF INCIDENT OR ACCIDENT**

Contracting party shall agree to promptly disclose to Nibley City, all incidents or occurrences of accident, injury, and/or property damage covered by the insurance policy or policies.

**D. OTHER INSURANCE PROVISIONS**

The policies are to contain, or be endorsed to contain, the following provisions:

I. General Liability and Automobile Liability Coverages

A. Nibley City, its officers, officials, employees and volunteers are to be covered as additional insureds as respects: liability arising out of activities performed by or on behalf of the contracting party; products and completed operations of the Contracting party; premises owned, leased, hired or borrowed by the Contracting party. The coverage shall contain no special limitations on the scope of protection afforded to Nibley City, its officers, officials, employees or volunteers.

B. The Contracting party's insurance coverage shall be a primary insurance as respects to Nibley City, its officers, officials, employees and volunteers. Any insurance or self‑insurance maintained by Nibley City, its officers, officials, employees or volunteers shall be in excess of the Contracting party's insurance and shall not contribute with it.

C. Any failure to comply with reporting provisions of the policies shall not affect coverage provided to Nibley City, its officers, officials, employees or volunteers.

D. The Contracting party's insurance shall apply separately to each insured against whom claim is made or suit is brought, except with respects to the limits of the insurer's liability.

**E. DEDUCTIBLES AND SELF‑INSURED RETENTIONS**

Any deductibles or self‑insured retention exceeding 5% of the policy limits must be declared to and approved by Nibley City. At the option of Nibley City, either (1) the insurer may be required to reduce or eliminate such deductibles or self‑insured retention as respects Nibley City, its officers, officials and employees; or (2) the Contracting party may be required to procure a bond guaranteeing payment of losses and related investigations, claim distribution and defense expenses.

**F. VERIFICATION OF COVERAGE**

Contracting party shall furnish Nibley City with certificates of insurance and with original endorsements effecting coverage required by this clause. The certificates and endorsements are to be signed by a person authorized by that insurer to bind coverage on its behalf. The certificates and endorsements are to be on forms acceptable to Nibley City before work commences. Nibley City reserves the right to require complete, certified copies of all required insurance policies, with all endorsements, at any time.

**G. SUBCONTRACTORS**

Contracting party shall include all subcontractors as insureds under its policies or shall furnish separate certificates and endorsements for each subcontractor. All coverages for subcontractors shall be subject to all of the requirements stated herein.

**PERFORMANCE AND PAYMENT BOND**

KNOW ALL MEN BY THESE PRESENTS, that we \_ as Principal, and , a corporation duly authorized to do a general surety business in Utah, as Surety, are jointly and severally held and bound unto . Hereinafter called the Obligee, in the sum of dollars ($) for the payment of which we jointly and severally bind ourselves, our heirs, executors, administrators, successors and assigns, firmly by these presents:

THE CONDITION OF THIS BOND IS SUCH THAT

WHEREAS, the Principal herein entered into a Contract with Obligee dated , 20 , which Contract includes and consists of Advertisement for Bids, Information for Bidders, Proposal, Special Provisions, General Conditions, Contract for Construction, Specifications and Plans, all of which are hereinafter referred to as Contract Documents and are attached hereto and made a part hereof and pursuant to the terms and conditions of all of which Principal has undertaken to perform all labor and to furnish all material, tools, and equipment of every kind and nature necessary or required in accordance with the terms and conditions set forth in said Contract Documents, and has undertaken to make payment promptly for all such labor (including all sums required to be paid by the laws of the State of Utah for the benefit and welfare of all workers, including workmen’s compensation and unemployment security), all taxes of every kind and nature, and for all materials and services furnished or rendered pursuant to such Contract: and,

WHEREAS, said Principal has agreed to save the Obligee harmless from any claim for damages and injury to property or persons arising by reason of said work, as set out more fully in said Contract Documents, and to do and perform all things in said Contract Documents required in the time and manner and under the terms and conditions therein set forth, and in conformity with all laws, State and National, applicable thereto.

NOW, THEREFORE, if the Principal shall promptly make payment to all persons supplying labor and material to Principal or to any subcontractor in the prosecution of the work provided for, and shall well and truly perform and fulfill all the undertakings, covenants, terms, conditions, and agreements of said Contract during the original term of said Contract and any extensions thereof that may be granted by the Obligee, with or without notice to the Surety, and shall also well and truly perform and fulfill all the undertakings, covenants, terms, conditions, and agreements of any and all duly authorized modifications of said Contract that may hereafter be made to Principal and/or to subcontractors, or their assigns, and shall, commencing with the date hereof and continuing for one (1) year after the complete performance of the Contract and the final settlement thereof, save harmless the Obligee, its officers and agents, from all claims therefore, or from any claim for damages or injury to property or persons arising by reason of said work; and shall, in the time and manner and under the terms and conditions prescribed, well and faithfully do, perform, and furnish all labor, materials, and things as by it in said Contract undertaken and as by law, State and National, prescribed, then this obligation shall be void, but otherwise it shall remain in full force and effect.

PROVIDED HOWEVER, that this Bond is subject to the following further conditions:

a) All material suppliers, and all persons who shall supply such laborers, mechanics, or subcontractors with material, supplies, or provisions for carrying on such work, shall have a direct right of action against the Principal and Surety on this Bond, second only to the right of the Obligee under this Bond, which right of action shall be asserted in proceedings instituted in the appropriate court of the State of Utah and insofar as permitted by the law of Utah, such right or action shall be asserted in a proceeding firm, or corporation instituting such action and of all persons, firms, or corporations having claims thereunder, and any other person, firm, or corporation having a claim hereunder shall have the right to be made a party to such proceeding, but not later than one (1) year after, the complete performance of said Contract and final settlement thereof and to have such claim adjudicated in such action and judgement rendered thereon.

b) In no event shall the Surety be liable for a greater sum than the penalty of this Bond, or subject to any suit, action, or proceeding thereon that is instituted later than one (1) year after the complete performance of said Contract and final settlement thereof.

c) The said Surety, for value received, hereby stipulates and agree that no change, extension of time, alteration, or addition to the terms of the contract or to the work to be performed thereunder or the Specifications accompanying the same shall in any way affect its obligations on this Bond, and it does hereby waive notice of any such change, extension of time, alteration, or addition to the terms of the Contract or to the work or to the Specifications.

IN WITNESS WHEREOF, the parties hereto have caused this Bond to be executed in , this day of , 20 .

(Seal)

(Seal)

(Seal)

Principal

Witnesses:

(Seal)

(Seal)

(Seal)

Surety

Countersigned:

By

Resident Agent

The Attorney-in-Fact (Resident Agent), who executes this Bond in behalf of the surety company, must attach a copy of their power-of-attorney as evidence of their authority.

**NOTICE TO PROCEED**

Date:

To:

Project: 1300 WEST IMPROVEMENTS

FROM 3310 SOUTH TO 3390 SOUTH

You are hereby notified to commence work in accordance with the Contract for Construction dated , 2025. The date of substantial completion of all work is , 2025, and the date of completion and readiness for final payment is , 2025. The Contract for Construction contains a liquidated damages clause for missed milestones, if any, and/or work unfinished by the above dates in the amount of [$1,500] per day.

Nibley City, Utah

By:

Title:

ACCEPTANCE OF NOTICE

Receipt of the above Notice to Proceed is hereby acknowledged.

By:

Title:

Date:

NIBLEY CITY

**CHANGE ORDER FORM**

CHANGE ORDER # : DATE

PROJECT NAME 1300 WEST IMPROVEMENTS

FROM 3310 SOUTH TO 3390 SOUTH

CONTRACTOR

DESCRIPTION:

Item Description Total

CHANGE ORDER AMOUNT $

TOTAL ADJUSTED CONTRACT AMOUNT $

TIME EXTENSION PER THIS CHANGE ORDER:

REVISED COMPLETION DATE:

Date City Engineer

Date City Manager\_\_\_\_\_\_

Date Contractor

**NOTIFICATION OF PROJECT COMPLETION**

PROJECT NAME AND LIMITS:

CONTRACTOR:

SIGNATURE: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

DATE: \_\_\_\_\_\_\_\_\_\_\_\_

This is to certify that as of the above date, all work connected with the above PROJECT, including BID items, CHANGE ORDER items, and PUNCH LIST items have been completed. We further certify that payment for any testing that was required by the project has been paid, including all bacteriological testing of pipe lines.

We hereby request that the Project Manager verify completion of the PROJECT

CONTRACTOR Signature: \_\_\_\_

DATE

(ABOVE TO BE COMPLETED BY THE CONTRACTOR)

- - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - -

(BELOW TO BE COMPLETED BY NIBLEY CITY)

DATE OF COMPLETION VERIFICATION: \_\_\_

(For verification of payment for bacteriological testing, call 753-5135 ext. 119 or 111)

CITY ENGINEER Signature: \_\_\_\_\_

DATE

PUBLIC WORKS DIRECTOR Signature:

DATE

**GENERAL CONDITIONS AND SPECIAL PROVISIONS**

TECHNICAL SPECIFICATIONS

As specified in the construction plans general and project specific notes.

STANDARD DRAWINGS

As specified in the construction plans general and project specific notes.

SPECIAL PROVISIONS:

1. There are documented wetlands adjacent to and within the project limits. CONTRACTOR shall prepare a SWPPP meeting local, state, and federal requirements in accordance with Bid Item #4. In addition to project site BPMs compliant with the Construction General Permit (CGP). CONTRACTOR shall install and maintain BMPs specific to protection of wetlands. CONTRACTOR shall perform and document site inspections once every 7 calendar days AND inspect within 24-hours after a storm event of 0.5 inches for greater in accordance with Section 4.1.3 of the CGP.
2. CONTRACTOR shall maintain access to residents, and property owners for the duration of the project. Property owners shall be notified at least 48-hours in advance of any restriction to access their properties.
3. CONTRACTOR shall familiarize themselves with the full construction plan set, especially the general notes and specific notes which take precedence over all conflicts.
4. CONTRACTOR shall familiarize themselves with all SPECIAL PROVISIONS which are incorporated as part of the CONTRACT FOR CONSTRUCTION.
5. Final quantities and project locations will be dependent upon bids and the final budgets.
6. Nibley City owns the properties within the work area that is available for staging, storage, and stockpiling materials.